## Sheet1
Phase | Task Description | Dates | Assigned Person | Depends On | Tracking
1. Requirement Gathering | Identify core features (CRUD posts, authentication,favorites, image uploads, etc.) | 24-30April | All Team |  | Done
2. Flowchart & Mindmapping | Visualize flow of user roles, access control, and feature interactions | 12-15 May | All Team | Requirement Gathering | Done
3. DB Schema Designing | Design DB tables, relationships | 31May-1June | Pooja Jagtap | Flowchart & Mindmapping | Done
4. ER Diagram | Create ER diagram based on schema | 2025-06-01 | Pooja Jagtap | DB Schema Designing | Done
5. UI/UX Designing | Create wireframes /mockups for UI | 1-2June | Divya Gatkal | DB Schema Designing
6. Frontend | Build pages with form validation, user roles (Admin/User), responsiveness | 3-6June | Divya Gatkal | UI/UX Designing
7. Backend | Set up server, routes, DB connection | 7-12June | Pooja Jagtap | DB Schema Designing
8. API Integration | Connect frontend to backend using APIs | 12-15June | Pooja Jagtap | Frontend & Backend
9. Testing & Bug Fixing | Functional & UI testing, bug resolution | 16-18June | Divya Gatkal | API Integration
10. Deployment | Deploy app to cloud (e.g., Vercel/Render /Netlify) | 2025-06-19 | Divya Gatkal | Testing & Bug Fixing
11. Documentation & Final Review | Prepare report, present to mentors | 2020-06-01 | All Team | Deployment